## NullBreach Gantt Chart
PROJECT: INVENTORY MANAGEMENT SYSTEM Thrifted & Branded Surplus Clothing – Development Gantt Chart
PROJECT TITLE | Inventory Management System for Thrifted & Branded Surplus Clothing |  |  |  | START DATE |  | 2026-09-07
TEAM | SQ-Way ¦ Weeks 4–14 |  |  |  | END DATE |  | 2026-11-22
[5 empty] | DURATION |  | 77
LEGEND: | ▬ Complete ▬ Not Started ▬ In Progress
WBS | TASK NAME | STATUS | ASSIGNED TO | START | END | DAYS | TASK ID / WEEKS | STATUS | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14
[9 empty] | Sep 7–13 | Sep 14–20 | Sep 21–27 | Sep 28– Oct 4 | Oct 5–11 | Oct 12–18 | Oct 19–25 | Oct 26– Nov 1 | Nov 2–8 | Nov 9–15 | Nov 16–22
1 | PHASE 1: PLANNING & REQUIREMENTS | Complete |  | 2026-09-07 | 2026-09-20 | 14 | Week 4 - 5 | Complete
1.1 | – Project Planning & Documentation | Complete | Project Manager & System Analyst | 2026-09-07 | 2026-09-13 | 7 | IMS-01-01 | Complete
1.1.1 | –– Finalize Project Topic & Scope | Complete | Project Manager | 2026-09-07 | 2026-09-08 | 2 | IMS-01-01-01 | Complete
1.1.2 | –– Draft Development Plan & Timeline | Complete | Project Manager | 2026-09-09 | 2026-09-10 | 2 | IMS-01-01-02 | Complete
1.1.3 | –– Process Flow & Process Analysis | Complete | System Analyst | 2026-09-10 | 2026-09-12 | 3 | IMS-01-01-03 | Complete
1.1.4 | –– Draft Test Plan | Complete | QA & Tester | 2026-09-11 | 2026-09-13 | 3 | IMS-01-01-04 | Complete
1.2 | – Requirements Analysis | Complete | System Analyst | 2026-09-14 | 2026-09-20 | 7 | IMS-01-02 | Complete
1.2.1 | –– Gather Needs of Staff, Reviewer & Admin | Complete | System Analyst | 2026-09-14 | 2026-09-16 | 3 | IMS-01-02-01 | Complete
1.2.2 | –– Document Functional Requirements | Complete | System Analyst | 2026-09-16 | 2026-09-18 | 3 | IMS-01-02-02 | Complete
1.2.3 | –– Document Non-Functional Requirements | Complete | System Analyst | 2026-09-18 | 2026-09-20 | 3 | IMS-01-02-03 | Complete
2 | PHASE 2: ANALYSIS & DESIGN | Complete |  | 2026-09-21 | 2026-10-04 | 14 | Week 6 - 7 | Complete
2.1 | – System Analysis & Design | Complete | System Analyst & UI/UX Designer | 2026-09-21 | 2026-09-27 | 7 | IMS-02-01 | Complete
2.1.1 | –– Finalize Item Status Flow | Complete | System Analyst | 2026-09-21 | 2026-09-23 | 3 | IMS-02-01-01 | Complete
2.1.2 | –– Define User Roles & Permissions | Complete | System Analyst | 2026-09-23 | 2026-09-24 | 2 | IMS-02-01-02 | Complete
2.1.3 | –– Use Cases & Overall System Design | Complete | System Analyst | 2026-09-24 | 2026-09-27 | 4 | IMS-02-01-03 | Complete
2.2 | – Database & Interface Design | Complete | System Developer & UI/UX Designer | 2026-09-28 | 2026-10-04 | 7 | IMS-02-02 | Complete
2.2.1 | –– Database Design (Items, Users, Status Logs) | Complete | System Developer | 2026-09-28 | 2026-10-01 | 4 | IMS-02-02-01 | Complete
2.2.2 | –– UI Layouts (Login, Item Form, Pending Queue) | Complete | UI/UX Designer | 2026-10-01 | 2026-10-04 | 4 | IMS-02-02-02 | Complete
3 | PHASE 3: INTAKE, AUTHENTICATION & APPROVAL | In Progress |  | 2026-09-30 | 2026-10-17 | 18 | Week 8 - 9 | In Progress
3.1 | – Item Intake & Authentication | Complete | System Developer | 2026-09-30 | 2026-10-11 | 12 | IMS-03-01 | Complete
3.1.1 | –– Project Setup, Database Tables & Login Screen | Complete | System Developer | 2026-09-30 | 2026-10-04 | 5 | IMS-03-01-01 | Complete
3.1.2 | –– Role-Based Access Control | Complete | System Developer | 2026-10-05 | 2026-10-07 | 3 | IMS-03-01-02 | Complete
3.1.3 | –– Add Item Form (New Items = Pending) | Complete | System Developer | 2026-10-08 | 2026-10-11 | 4 | IMS-03-01-03 | Complete
3.2 | – Approval Workflow | In Progress | System Developer | 2026-10-12 | 2026-10-17 | 6 | IMS-03-02 | In Progress
3.2.1 | –– Pending Items Queue | In Progress | System Developer | 2026-10-12 | 2026-10-13 | 2 | IMS-03-02-01 | In Progress
3.2.2 | –– Approve / Reject Actions & Reason Capture | In Progress | System Developer | 2026-10-14 | 2026-10-15 | 2 | IMS-03-02-02 | In Progress
3.2.3 | –– Status Transition Logic | In Progress | System Developer | 2026-10-16 | 2026-10-17 | 2 | IMS-03-02-03 | In Progress
4 | PHASE 4: SALES, STOCK & REPORTS | In Progress |  | 2026-10-18 | 2026-10-25 | 8 | Week 9 - 10 | In Progress
4.1 | – Sales & Stock | In Progress | System Developer | 2026-10-18 | 2026-10-22 | 5 | IMS-04-01 | In Progress
4.1.1 | –– Sale / Checkout Screen | In Progress | System Developer | 2026-10-18 | 2026-10-19 | 2 | IMS-04-01-01 | In Progress
4.1.2 | –– Stock Tracking & Low-Stock Flagging | Not Started | System Developer | 2026-10-20 | 2026-10-21 | 2 | IMS-04-01-02 | Not Started
4.1.3 | –– Enforce Only In Stock Items Can Be Sold | Not Started | System Developer | 2026-10-21 | 2026-10-22 | 2 | IMS-04-01-03 | Not Started
4.2 | – Reports & Integration | Not Started | System Developer | 2026-10-22 | 2026-10-25 | 4 | IMS-04-02 | Not Started
4.2.1 | –– Inventory Search & Dashboard | Not Started | System Developer | 2026-10-22 | 2026-10-23 | 2 | IMS-04-02-01 | Not Started
4.2.2 | –– Reports Screens | Not Started | System Developer | 2026-10-23 | 2026-10-24 | 2 | IMS-04-02-02 | Not Started
4.2.3 | –– Module Integration & Status Logging | Not Started | System Developer | 2026-10-24 | 2026-10-25 | 2 | IMS-04-02-03 | Not Started
5 | PHASE 5: TESTING (SYSTEM TESTING & UAT) | Not Started |  | 2026-10-26 | 2026-11-08 | 14 | Week 11 - 12 | Not Started
5.1 | – System Testing (Postman Collection Automation) | Not Started | QA & Tester | 2026-10-26 | 2026-11-01 | 7 | IMS-05-01 | Not Started
5.1.1 | –– Build Postman Collection & Test Cases | Not Started | QA & Tester | 2026-10-26 | 2026-10-27 | 2 | IMS-05-01-01 | Not Started
5.1.2 | –– Run Collection via Newman (Functional, Integration & Status-Rule Tests) | Not Started | Tester | 2026-10-28 | 2026-10-30 | 3 | IMS-05-01-02 | Not Started
5.1.3 | –– Defect Logging & Test Report | Not Started | QA & Tester | 2026-10-31 | 2026-11-01 | 2 | IMS-05-01-03 | Not Started
5.2 | – User Acceptance Testing (UAT) | Not Started | QA, Tester & System Analyst | 2026-11-02 | 2026-11-08 | 7 | IMS-05-02 | Not Started
5.2.1 | –– UAT with Staff & Reviewer Roles | Not Started | Tester & QA | 2026-11-02 | 2026-11-04 | 3 | IMS-05-02-01 | Not Started
5.2.2 | –– Gather Feedback & Evaluate Usability | Not Started | System Analyst | 2026-11-05 | 2026-11-06 | 2 | IMS-05-02-02 | Not Started
5.2.3 | –– UAT Report & Test Sign-off | Not Started | QA | 2026-11-07 | 2026-11-08 | 2 | IMS-05-02-03 | Not Started
6 | PHASE 6: FINALIZATION & DEPLOYMENT | Not Started |  | 2026-11-09 | 2026-11-22 | 14 | Week 13 - 14 | Not Started
6.1 | – Defect Fixing, Final Testing & Deployment | Not Started | QA & System Developer | 2026-11-09 | 2026-11-19 | 11 | IMS-06-01 | Not Started
6.1.1 | –– Defect Fixing & Refinement (from Test & UAT Reports) | Not Started | System Developer | 2026-11-09 | 2026-11-13 | 5 | IMS-06-01-01 | Not Started
6.1.2 | –– Regression & Final Testing (Re-run Postman Collection) | Not Started | QA & Tester | 2026-11-14 | 2026-11-16 | 3 | IMS-06-01-02 | Not Started
6.1.3 | –– Deploy Completed System | Not Started | System Developer | 2026-11-17 | 2026-11-19 | 3 | IMS-06-01-03 | Not Started
6.2 | – Documentation & Presentation | Not Started | Project Manager & System Analyst | 2026-11-19 | 2026-11-22 | 4 | IMS-06-02 | Not Started
6.2.1 | –– Finalize Documentation | Not Started | System Analyst | 2026-11-19 | 2026-11-20 | 2 | IMS-06-02-01 | Not Started
6.2.2 | –– Present Deployed System | Not Started | Project Team | 2026-11-21 | 2026-11-22 | 2 | IMS-06-02-02 | Not Started

## Lists
STATUS | ASSIGNED TO | To add a new option, type it in the next empty cell under the list. The dropdowns pick it up automatically.
Not Started | Project Manager
In Progress | System Developer
Complete | UI/UX Designer
QA
System Analyst
Tester
Project Team
Project Manager & System Analyst
QA & System Developer
QA & Tester
QA, Tester & System Analyst
System Analyst & UI/UX Designer
System Developer & Tester
System Developer & UI/UX Designer
Tester & QA